- INTER-AMERICAN COMMISSION OF WOMEN

EXECUTIVE COMMITTEE 2010-2012	OEA/Ser.L/II.5.31

FIRST REGULAR SESSION	CIM/CD/doc.6/11

Washington, D.C.	9 February 2011

7-8 April, 2011		Original: Spanish

CIM BIENNIAL PROGRAM OF WORK

2011-2012

CONTENTS

I.	INTRODUCTION	1

II.	CONTEXT	1

III.	PROGRAMMATIC AREAS AND ACTIVITIES BY RESULTS	4

IV.	IMPLEMENTATION STRATEGY	9

- INTRODUCTION

The CIM Biennial Program of Work 2008-2010 brought progress in the implementation of priority objectives set by the XXXIV Assembly of Delegates in November 2008, within the framework of the “Inter-American Program on the Promotion of Women's Human Rights and Gender Equity and Equality” (IAP). This period coincided with a change of management and leadership in the CIM Secretariat (August 2009) as well as institutional adjustments in the OAS in response to its financial difficulties.

Pursuant to General Assembly resolution AG/RES. 2322 (XXXVII-O/07), in 2010 the hemisphere celebrated the “Inter-American Year of Women” with the motto “Women and power.” Most OAS member states have carried out a range of activities that have drawn attention to the persistent inequality and underrepresentation of women in the region in political institutions and decision-making bodies.

In follow-up to the mandates of the CIM and taking into account the recent evaluations of both the IAP and the Follow-up Mechanism the Belem do Para Convention (MESECVI, CIM/CD/doc.24/10), as well as internal consultations on institutional priorities carried out with various OAS secretariats, the CIM Biennial Program of Work 2011-2012 with the aims of enhancing linkage and harmonization of CIM activities with those of the OAS, and institutionalizing a rights- and gender-equality-based approach in the main forums, programs, and plans of the Organization, as well as the positioning of CIM as a hemispheric policy forum and benchmark for the construction of women’s full citizenship, from a human rights perspective.

The CIM Biennial Program of Work 2011-2012 will be implemented from a perspective of strengthening human rights and building women’s citizenship. It will take into account the Consensuses of Quito and Brasilia, as well as the mandates generated through the Declaration of the Inter-American Year of Women. The Program will harvest the lessons learned from implementation of the 2009-2010 Program of Work, as well as other recently implemented activities and projects.

# CONTEXT

Over the last three years, the economies of the countries of the Americas have been hit by one of the worst financial crises in a century which, according to a number of recent studies, has had a greater adverse effect on women, particularly poor women.  These differences and disparities in the impact of the crisis are affecting economic and social opportunities for women, as well as the levels of quality of life achieved in the previous period. Even though the impact of the economic crisis has struck countries to varying degrees, it has been suggested that the progress achieved in poverty reduction and social-service coverage for low-income sectors of the population in the years prior to the crisis could be reversed if policies and levels of investment are not maintained.

On the other hand, significant strides have been made in the region with regard to women's access to the highest position of political representation in a country, namely, the presidency. In the last five years, four women have assumed the leadership of their countries: as presidents in Argentina, Brazil, Chile, and Costa Rica, and as prime minister in Trinidad and Tobago. This shows that women have been recognized as a real political force and an alternative for providing the effective leadership sought by citizens to solve their day-to-day problems, as well as to revitalize the process of building democratic citizenship in the region’s countries. Parity in the political inclusion of women continues to be conditioned and impeded by multiple gender inequality factors. A reminder of this is the fact that, apart from Chile it has been the countries that have most progressed in terms of application of quota laws where women have succeeded in becoming the head of state or government. Such is the case of Argentina and Costa Rica, where women have attained a high level of political representation, both in parliament and in local government: Argentina with 41.6% and Costa Rica with 36.8%./ The coincidence between a greater number of women in high-level, decision-making positions at both the governmental level and within international and regional organizations should be leveraged to advance women’s political agenda.

The full exercise of citizenship rights for women is essential for the construction of a citizens’ democracy and for good governance that is inclusive of 50% or more of the population. Women have had an active hand in the region’s democratization processes and in the grassroots mobilization that has made it possible to restore democratic governance in the majority of countries. Therefore, their political inclusion, based on their specific needs and interests, is a seminal aspect of citizens’ democracy and of the reforms of political institutions and of the State needed to achieve that.

During the last OAS General Assembly, the member states reaffirmed their commitment to the implementation of the “Inter-American Program on the Promotion of Women's Human Rights and Gender Equity and Equality” (IAP).  The IAP has helped to gradually include, albeit to a limited extent, the gender equality agenda in the activities of a number of OAS offices.  As the IAP evaluation report notes, its effective implementation requires setting operational goals and implementing results-based management mechanisms and instruments, including monitoring and evaluation, in order to weigh and follow-up on measures and efforts carried out in the OAS as well as in member countries.

Bearing in mind the challenges posed by the new hemispheric and institutional context, and based on the mandates of the CIM, including the decisions adopted by the Executive Committee in February 2010, a CIM Strategic Plan for 2011-2016 was prepared.  In addition to providing a platform for action, the plan will allow CIM to operationalize the IAP and to articulate its work with that of the national machineries for the advancement of women and with key regional and international bodies. Moreover, the Strategic Plan provides the basis for strengthening the continuous operation of CIM and its positioning as a benchmark for hemispheric policy on women’s human rights and gender equality.

IAP

CIM Strategic Plan 2011-2016

Gender in the four OAS pillars:

Democracy

Human rights and violence

Development

Security

CIM Biennial Program of Work 2011-2012

Activities

Awaited outcomes

Operational matrix

2011, 2012, 2013…

Activities

Awaited outcomes

Deadlines

Responsibilities

CIM operational goals and annual budget

Hemispheric and institutional context

Evaluation results

At the institutional level, in recent years, the OAS has undergone a realignment and budgetary adjustment process.  The Organization is facing a hefty budget deficit that entails significant funding restrictions for CIM plans, programs, and projects.  If progress in implementation of the PIA, CIM strategic plan for 2011-2016, and the other CIM mandates is to continue, adequate resources are needed.  This requires the CIM to step up its efforts effectively to mobilize funds, which will need active and resolved backing from OAS member states and observer countries, as well as reaching out to other donors.

The CIM is working on four issues connected with the four pillars of the OAS.  These are core themes of the Strategic Plan of Action and are as follows:

- Women's substantive political citizenship for democracy and good governance

- Women's human rights and violence

- Multidimensional security under a rights-based and gender-equality approach

- Women's security and economic citizenship

- PROGRAMMATIC AREAS AND ACTIVITIES BY RESULTS

  - Women's substantive political citizenship for democracy and good governance:

    - Progress, under a cooperation agreement, in the institutionalization of a rights-based and gender-equality approach in the most strategically important areas of the OAS Secretariat for Political Affairs:

- Engage the staff of the OAS Secretariat for Political Affairs in dialogue (regular and specific funds).

- Present the document prepared by the CIM on political reform and political rights of women, as well as on the public policies in force in this regard in the member countries of the Organization (regular and specific funds).

- Identify areas/measures for collaboration and prepare a common work agenda to advance political citizenship for women in all their diversity (specific funds).

    - Technical contributions to the process of design, development, and validation of an OAS working procedure for electoral observation missions (EOMs) to include coverage of women's citizenship and political rights:

- Technical advisory services to the OAS Department of Electoral Cooperation and Observation (DECO) in the design of a working procedure for EOMs (specific funds).

- Collaborate in workshops with counterpart agencies in the project (specific funds).

- Assist in the validation of the OAS EOM working procedure in the selected countries and as requested by DECO (specific funds).

- Review the analysis and guidelines which will be drawn up to guide EOM observers (specific funds).

- Follow-up the previous work of CIM on supporting the implementation of quota laws and other special measures to promote parity and diversity in political representation, in collaboration with International IDEA (specific funds).

    - Training and skills development for professionals in member states on the exercise of leadership in dialogue processes, consensus-building, and policy design, in order to influence the contents of the agenda on gender rights and equality:

- Hold on-site leadership training courses for influencing public policy (specific funds).

- Develop a course program for on-site and virtual leadership training courses for influencing public policy (specific funds).

- Hold two virtual training courses through the OAS Educational Portal, with specific emphasis on the participation of young women (specific funds).

- Prepare a proposal for an in-person course on leadership for incidence in public policy targeted specifically to young women (specific funds)

    - Contribution to the construction of a citizens’ democracy based on the visions and experiences of women in all their diversity:

- Prepare a four-year funding proposal for the CIM hemispheric policy forum with a view to its presentation to suitable donors (regular funds).

- Plan the first hemispheric forum on policy reform and substantive political citizenship for women (specific funds).

- Promote a hemispheric agenda on women's political citizenship and their increased political representation (specific funds).

- Hold a dialogue on progress and shortcomings in the implementation of the Inter-American Democratic Charter as regards attainment of “full and equal participation of women in the political structures of their countries” (regular and specific funds).

  - Submit the report that the IACHR is to prepare on the situation of women's political rights in the Hemisphere, and the document of the CIM on political reform and women's political rights, as well as public policies in force in this area in OAS member countries (specific funds).

  - Present the OAS/UNDP conceptual document on citizens’ democracy and discuss from the perspective of women’s substantive political citizenship (specific funds).

  - Systematize the results of the forum in a conceptual/political document on a citizens’ democracy for women’s political rights (specific funds).

- Prepare a project proposal to work with political parties of the region on: i) increasing women’s participation, particularly in leadership positions; and ii) strengthening the representation of women’s agenda within the platforms of these parties, in collaboration with International IDEA (regular funds).

- Organize, in collaboration with International IDEA, a hemispheric forum on women and political parties in the Americas (specific funds).

- Promote the reform of electoral legislation and affirmative action measures to foster equal treatment between women and men in political representation and promote legislation and specific measures that ensure the elimination of obstacles that women face in political party activity, electoral campaigns and access to public financing.

    - Capacity-development on gender-sensitive governance at the local level

      - Support the preparation of gender budgets at the municipal level, in collaboration with UN Women and other relevant partners.

  - Women’s Human Rights and Violence

    - Capacities of the National Mechanisms for the Advancement of Women's Rights and women's networks strengthened in order to comprehensively monitor the exercise of women's rights in selected countries, as well as the workings, indicators, and procedures of the inter-American system for protection of human rights, under a cooperation agreement with the Inter-American Commission on Human Rights (IACHR) and the Inter-American Institute of Human Rights (IIDH):

- Design a proposed training program with the IACHR and IIDH (regular fund and specific funds).

- Carry out training activities in selected countries on methodological and conceptual frameworks to monitor the exercise of women’s human rights, as well as training on the operation, indicators and procedures of the Inter-American system of human rights (specific funds).

- Develop a virtual training course on this issue on the OAS Educational Portal (specific funds).

    - Start of a process by which to identify a baseline for monitoring the extent, incidence, prevalence, and characteristics of violence against women and girls in the countries of the Americas:

- Prepare a project proposal to secure funding for the establishment of a baseline to evaluate the impact of the application of the Convention of Belem do Pará in women’s lives (regular funds).

- Present the proposal to donors that regard this issue as a priority (specific funds).

- Prepare a study on the implementation status of the Convention of Belem do Pará after 15 years of existence as an input for the baseline study (specific funds).

    - Sustained operation of the Follow-Up Mechanism for the Inter-American Convention on the Prevention, Punishment, and Eradication of Violence against Women, "Convention of Belém do Pará” (MESECVI):

- Prepare a five-year project proposal for the operation and strengthening of MESECVI (regular funds).

- Organize relevant meetings of the CEVI and of the States Party (specific funds).

- Prepare the summary minutes of CEVI meetings and the Hemispheric Report at the end of each Multilateral Evaluation Round (specific funds).

- Attend to, inform and respond continuously to the individuals and organizations involved in the MESECVI (specific funds).

- Hold a joint seminar on femicide with American University (specific funds).

- Organize a working group of member states to prepare a proposal to the Committee on Administrative and Budgetary Affairs (CAAP) of the Permanent Counsel for the establishment of a permanent budgetary allocation from the regular fund of the OAS for the MESECVI (regular funds).

    - Strengthening of the Follow-Up Mechanism for the Inter-American Convention on the Prevention, Punishment, and Eradication of Violence against Women, "Convention of Belém do Pará” (MESECVI)

    - Strengthen the institutional capacity of the CIM, in its role as the technical secretariat of the MESECVI, to contribute to the effective implementation of the Belém do Pará Convention.

    - Foster the support of member states and the OAS General Secretariat for the mobilization of qualified human resources for the MESECVI Technical Secretariat (regular and specific funds)

    - Design and launch the MESECVI website (specific funds).

  - Women's security and economic citizenship

    - Promote the integration of a rights-based and gender equality approach in OAS fora:

- Carry out, in cooperation with the Department of Economic Development, Trade and Tourism of the OAS, a study in six countries in the region on the way in which MSME support policies take into account gender-conditioning factors and ensure equality for women in terms of access to the resources and services covered by these policies.  Based on this study, formulate recommendations and strategies that can be integrated with said policies (specific funds).

- Hold a dialogue or dialogues on gender equality in MSME and competitiveness policies in the framework of meetings of competitiveness authorities and councils in OAS member states (specific funds).

- Design a regional project proposal for integration of a gender perspective in OAS activities to increase competitiveness and productivity in sustainable development (regular funds).

    - Promotion of the institutionalization of a rights-based and gender-equality approach in decent work, in follow-up to the “Strategic Guidelines for Advancing Gender Equality and Non-discrimination within a Decent Work Framework,” issued by the XV Inter-American Conference of Ministers of Labor (IACML), under a cooperation agreement with the Secretariat for Integral Development:

- Hold a high-level dialogue or dialogues on gender inequalities in the workplace, bringing together labor ministries and national mechanisms for the advancement of women of member states.  These dialogues would be convened with the OAS Department of Social Development and Employment (DSDE) (specific funds).

- Draft a project proposal for the continuation of the activities of the current project “Advancing Gender Equality in a Decent Work Framework,” in coordination with the DDSE and the International Labor Organization (ILO) (specific funds).

- Contribute at meetings of the IACML working groups, in particular those that follow up on the strategic guidelines on gender equality and decent work, and in preparation for the XVII IACML (El Salvador, 2011) (specific funds).

- Prepare a publication that includes the working procedure, results, and lessons learned from subregional training workshops on strategic planning with a gender perspective held in 2010 in the decent work framework (specific funds).

  - Multidimensional security under a rights-based and gender-equality approach

    - Progress in the institutionalization of a rights-based and gender-equality approach under a cooperation agreement with the Secretariat for Multidimensional Security in the follow-up activities on the Declaration on Security in the Americas:

- Conduct a needs assessment, i) in the OAS; and, ii) with the relevant government departments and security agencies of selected countries, with a view to the incorporation of a rights-based and gender-equality approach in their work (specific funds).

- Produce and distribute informative, awareness, and training materials in response to wants and needs identified in assessments, in a bid to facilitate integration of a rights-based and gender-equality approach as well as female participation in the security sector (specific funds).

    - Develop a position paper on multidimensional security from a rights-based and gender-equality perspective that provides a basis for guiding public-policy dialogue in this area.

    - Contribution to the construction of multidimensional security with a rights-based and gender-equality approach that takes into account the perspectives and experience of women:

- Organize in the context of OAS-managed forums a high-level meeting on democratization of the security sector from a gender-based perspective, attended by national mechanisms for the advancement of women and representatives of the relevant ministries (specific funds).

- Establish an ongoing (virtual) dialogue mechanism to follow up on the results of the meeting so as to include different perspectives in the discussion (civil society, academia, private sector, etc.) (specific funds).

  - Sustaining and strengthening the work of the Inter-American Commission of Women (CIM)

    - Sustained operation of CIM

- Provide technical, logistical, and administrative support for the work of the Chair of the CIM in the performance of her official functions (regular funds)

- Prepare the preliminary draft program-budget of the CIM (regular funds)

- Permanently provide assistance, information, and responses to the various interlocutors and bodies involved (Principal Delegates of the CIM, Permanent Missions to the OAS (of member and observer countries), OAS General Assembly, Summit Implementation Review Group, etc.) (regular funds).

- Organize the Thirty-sixth Assembly of Delegates (2012), the 4th REMIM (in 2012) and three meetings of the Executive Committee of the CIM (preparation and distribution of notices, reports, minutes, documents, and translations, etc.) (regular funds).

- Represent the CIM and the OAS whenever needed and prepare the respective presentations or documents (regular funds).

- Administer the regular and specific funds of the CIM and MESECVI, as well as prepare financial reports as requested by the General Assembly (regular funds).

    - Project/program proposals prepared for securing specific funds:

- Prepare in each thematic area of work at least one program proposal for distribution to suitable donors, in cooperation with the appropriate Secretariat (regular funds).

    - Increase the visibility of the CIM through the launch of a new website and specific communication initiatives.

  - Launch a CIM website in Spanish and English (regular funds).

  - Design and implement a communication strategy for the CIM (regular funds).

    - Strengthened coordination between the CIM and stakeholders in member states, civil society, the academic sector, the international community, and the private sector through cooperation agreements:

- Design and implement a CIM strategy for networking and for incidence in key forums and spaces based on a stakeholder assessment and through specific cooperation agreements (regular funds).

- Renew the collaboration agreement between the OAS and UN Women (previously signed with UNIFEM) and establish a joint activity plan that leverages the comparative advantages of each organization (regular funds).

- Strengthen articulation and the permanent dialogue with civil society, identifying and launching a specific mechanism to strengthen their role in the CIM (regular funds).

  - Institutionalization of a rights-based and gender equality approach in the work of the OAS

    - Bring a rights-based and gender equality approach to the four priority pillars of the work of the OAS, to its main hemispheric forums and networks and to the project development and implementation process.

        - Prepare a project proposal to follow-up the “Incorporation of gender analysis and gender equity and equality as crosscutting topics and objectives in all OAS programs” project and support the implementation of the IAP in a cross-cutting manner throughout the OAS.

        - Establish the OAS Gender Community of Practice with the aim of fostering dialogue and technical support among Departments for the institutionalization of a rights-based and gender equality approach.

- IV.	IMPLEMENTATION STRATEGY

The main implementation strategies for the CIM Work Program for the 2011-2012 Biennium are as follows:

  - Coordination and linkage of program activities with the relevant OAS Secretariats for accomplishing its results.

  - Strengthening of the institutional capacities of the CIM to implement the PIA, the 2011-2016 Strategic Plan, and the Work Program for the 2011-2012 Biennium, as well as to monitor their implementation within the OAS under a results-based management approach.

  - Fundraising from bilateral and multilateral donors.

  - Coordination and creation of strategic partnerships with international cooperation agencies that work in the area of women's rights and gender equality.

  - Creation of strategic partnerships for management of networks of women's and academic organizations.

  - CIM financial and human resources

For the period 2011-2012, the budget for the CIM Secretariat is a total of US$474,000 (US$237,000 per year).  These funds will cover the following specific activities:

    - Mandatory institutional meetings:

      - Three formal sessions of the CIM Executive Committee (April and autumn 2011, spring 2012)

      - The fourth REMIM (Meeting of Women Ministers, autumn 2011)

      - The 36th Assembly of Delegates (autumn 2012, Costa Rica)

    - Other meetings, to be determined (including informal sessions of the CIM Executive Committee and meetings of the CEVI and States Party of the MESECVI)

    - Publications (layout and printing of documents)

    - Telephones, photocopies, etc.

    - Acquisitions (office supplies and equipment)

    - Consultancy and provider contracts to meet specific needs (logistical support, information-gathering, preparation of documents, etc.)

    - Travel of the CIM President and Secretariat personnel to official meetings.

The personnel of the CIM Secretariat includes, at this time, one Executive Secretary, four professional-level staff members and one administrative staff member.  In addition, the Secretariat has a fluctuating number of consultants and interns, provided by the OAS Internship Program.

input.doc

-  All received comments have been underlined in this text.

- .  See: Bárcena, A., “El impacto de la crisis financiera sobre las economías de América Latina y el Caribe y repercusiones previsibles sobre las mujeres.” Presentación Turing the Expert Group Meeting on  “Analysis of the economic and financial crisis from a gender perspective: Understanding its impacto on women’s work.” Mexico City, July 23-24, 2009); and Mones, B. “Las políticas de estimulo económico frente a la crisis y las oportunidades para las mujeres de Latinoamérica.” New York: UNIFEM, 2010 (forthcoming).

- .   Proposed by UNDP and the OAS turing the First Forum on Democracy in Latin American (Mexico City, October 12th to 14th, 2010), the concept of a citizens’ democracy requires citizenship training in order to ensure that votes are informed, conscious and reflect a political position.  Citizens’ democracy is defined in contrast to representative electoral democracy, in the sense that it seeks to support the full participation and citizenship of all,, through the elimination of the economic and social inequalities that impede the exercise of that citizenship.  From the perspective of women, a citizens’ democracy implies in-depth questioning of the nature and operation of current democratic systems, from the basis of parity in leadership, representation and participation.  Source: UNDP and OAS. Our Democracy. Mexico: FCE, UNDP and OAS, 2010. http://www.nuestrademocracia.org/

- .  IPU, 2009.

- . Citizenship rights are those civil, political, economic, social and cultural rights – human rights – that every democracy should guarantee and promote. Source: UNDP and OAS, 2010.

- .  The organization of meetings includes the following specific expenses: preparation, translation and printing of documents in four languages, simultaneous translation in four languages, conference services (room assistants, electronic equipment, videoconference, Webcasting and audio/video recording services, hospitality, etc.) and other specific expenses (preparation of reports, expert presentations, etc.)