CIE and Technical Secretariat Comments and Questions for the Evaluation Forum

# CIE Comments and Questions

The CIE has the following comments and questions for the Evaluation Forum Project proposal.

- This proposal needs to be resubmitted using the appropriate CIE format.

- The project requests an usually high amount of sub-funds, especially for travel related expenses; however, the proposal lacks details on exactly how the sub-funds would be distributed among the project’s activities.

- Proposal should explain more fully the project’s objectives and rationale.

- There exist reservations and concerns with the project’s emphasis on a single assessment model.  Is this actually possible or feasible to all member states’ contexts?

- There needs to be a mechanism developed for project monitoring and evaluation.

- There appears to be some overlap with PRIE.  Would it be possible to coordinate with PRIE to form one comprehensive project?

- The project proposes working with the Caribbean region to improve their educational assessment systems; however, a baseline assessment study is necessary before proceeding further.  Please describe the proposed baseline assessment study, if any.

- Please clarify the budget.

# Technical Secretariat Comments and Questions

The Technical Secretariat has the following comments and questions for the Evaluation Forum Project proposal.

- The proposal does not use the appropriate CIE format.  Please resubmit using the CIE

format for project proposals.

- The proposal outlines activities from 2005.

- Approximately 75% of the sub-funds requested are slated to be used for travel related expenses; 18% towards contracts; 7% for other project activities.

- It appears that the training component included as part of the project’s activities does not include information about the progress and advances member states have made in their national and sub-national educational assessment systems.

- The project proposes using a single model of evaluation and assessment that may or may not be conducive to the needs and particular contexts of all member states.  Is this realistic or feasible?

- There appears to be little mention of PRIE, except for inviting personnel from PRIE to the meetings.  However, the proposal needs to make more clear how the project supports PRIE in identifying educational indicators that address issues of quality and education system performance.

- The project activities need to specify how they correspond to the overall goals and objectives.