OEA/Ser.G

CP/doc. 3825/04 add. 1

9 February 2004

Original:  English

QUARTERLY REPORT ON THE USE OF FUNDS
ALLOCATED UNDER RESOLUTION CP/RES. 831 (1342/02)
BETWEEN OCTOBER 1 AND DECEMBER 31, 2003

Fund for Peace

- This document is being distributed to the permanent missions and
will be presented to the Permanent Council of the Organization.

.

USE OF EXCESS RESOURCES OF THE RESERVE SUBFUND FOR CAPITAL INVESTMENTS AND TO MEET OAS MANDATES

QUARTERLY REPORT TO THE PERMANENT COUNCIL ON ACTIVITIES OF THE FUND FOR PEACE FOR THE PERIOD OCTOBER 1 – DECEMBER 31, 2003

Permanent Council Resolution 831 (1342/02) paragraph 1. e. resolves to appropriate “one million dollars (US$1,000,000) which shall be allocated to the Fund for Peace: Peaceful Settlement of Territorial Disputes”.

To this end, the Office of the Assistant Secretary General, responsible for the Fund for Peace, is pleased to provide the Permanent Council with the following information:

Beginning balance as of January 1, 2003:		$1,000,000.00

Interest earned as of Dec, 31, 2003:			$     17,622

Amount spent and already reported in

previous quarter (July 1-Sep. 30, 2003)			($      2,416)

Amount spent during this quarter			($      9,577)

Amount obligated but not expended			($      1,484)

Balance as of December 31, 2003			$1,004,145

Expenditures for October 1- December 31, 2003:

During the period September 30 to December 31, 2003, US $9,577 was expended. The amount corresponds to costs related to a preparatory work undertaken by the Office of the General Secretariat in the Adjacency Zone between Belize and Guatemala, in compliance with the Agreement to Establish a Transition Process and Confidence Building Measures between Belize and Guatemala, signed by the Foreign Ministers of both countries and by the General Secretariat on February 7, 2003, which instructs the Secretariat to design a resettlement project in the Adjacency Zone between Belize and Guatemala.

The expenditures during this period were for travel expenses of a team of experts from the Office of the General Secretariat in Nicaragua and from OAS Headquarters in Washington, which made an assessment of the resettlement project; the per diem costs of one of the experts from Nicaragua who stayed in the Adjacency Zone from September to December to supervise and manage the start-up of the resettlement project; the cost of a topographic study of the area where the resettlement is to be constructed; salaries of local workers who prepared the land and the area for the construction; and the purchase of various construction materials.

ANNEX

First General Expenditure:  Travel and per diem costs:  Total cost was $4875.65

Specific Activities undertaken and corresponding cost:

1) Travel: ticket fare, per diem and terminal expenses for a 3 expert team from Nicaragua to Belize from Sep 28 –Oct 1, 03.   Cost $2,671.65

2) Per diem costs of one expert from Nicaragua, working on an extended assignment in the Adjacency Zone between Belize and Guatemala, from end of September to beginning of December, 2003.  Cost $2,204.00

Results Achieved:    The OAS team of specialists from Nicaragua, with experience in building large housing projects in Central America following the 1998 Hurricane “Mitch”,  supported the General Secretariat in terms of assessing the costs, timeframe, feasibility of the terrain, labor force and construction materials necessary, in order to proceed with a resettlement project in the Adjacency Zone between Belize and Guatemala, in compliance with the Agreement to Establish a Transition Process and Confidence Building Measures between Belize and Guatemala, signed by the Foreign Ministers of both countries and by the General Secretariat on February 7, 2003.

input.doc

Second General Expenditure: Construction related costs and preparation of the area for the resettlement $4,700.99

Specific Activities undertaken and corresponding cost:

1) Purchase of construction materials such as wood, chemical treatment, wire, etc.  Cost $1,115.59

2) Payment of salaries of local workers.  Cost $2,491.65

3) Topographic study of the area.   Cost $385.00

4) Transportation costs (truck rental for 2 weeks).  Cost $708.75

Results Achieved:  This expert from Nicaragua ensured the completion of the preparatory work for the resettlement project, including terrain preparation, the purchase of construction and other related materials and to the hiring of local labor personnel required to work on the terrain.

.	Based on information provided by the Office of the Undersecretary for Management on February 9, 2004.

.	Ibid.